## Instructions
SE Lab Assignment 1 Team Workbook
Smart Ticketing System (TVM) ¦ Sem 1_2627 ¦ One workbook per group, kept in your shared folder and in your GitHub repository
Purpose
This workbook is your group's working record for Lab Group Assignment 1. It contains the Clarification Q&A and the requirements (two deliverables you hand in as Excel or Word), plus trackers that show your process: who built what, the diagrams and their status, your Copilot prompts, your commits and your weekly progress. The lecturer reads it during the labs and replies in the green cells. Student self-marking and lecturer marking are on the Marking sheet. It supports, and does not replace, your official submission (the .docx report, readme.txt and the % contribution).
How to use it
1. Fill in the Team sheet first (3 to 5 students, % contribution totalling 100%).
2. Do the Clarification Q&A before you write the requirements. Every assumed answer should lead to a requirement ID.
3. Update the Artifact Tracker, Commit Log, AI Prompt Log and Progress Log every lab week. These show the process mark evidence.
4. Before submission, use the Consistency Check sheet, then self-mark on the Marking sheet. The lecturer marks in the green column.
Colour legend
Student input | Yellow fill, blue text
Lecturer input | Green fill, blue text
Calculated / fixed | Black text, no fill
Sheets in this workbook
Sheet | What it is for | Report section it feeds | When to fill in
Team | Members, roles, % contribution, commit counts | 1.3, 7 | Week 1
Clarification Q&A | Ambiguities, questions and assumed answers (Task 1, 5%) | 2.1 | Before requirements
Requirements | Functional, non-functional and domain requirements with measurable metrics (Task 2, 15%) | 2.2 | Phase 1
Use Cases | Use case register and description status (Task 3) | 3.1 | Phase 2
Artifact Tracker | Every deliverable: owner, tool, link, status, % done | All | Throughout
Consistency Check | Alignment of the diagrams and the code | 3.4 | Before submitting
AI Prompt Log | Copilot prompts, how the AI helped, how you validated (Task 9) | 5.2.2 | Throughout
Commit Log | Commits and pull requests per member per week | 5.2.1 | Weekly
Progress Log | Weekly plan, actual work, evidence and lecturer feedback | Process mark | Weekly
Marking | Self-mark and lecturer mark for the 10 tasks (100%) | – | End
Summary | Group result, QT2 points and individual marks | – | End

## Team
Team and Contribution
Group of 3 to 5 students. The % contribution of each member must total 100% and match your readme.txt.
Group name
GitHub repo | https://github.com/Nghiaktvn/SE-Lab-QT2-Assignments
Group size | 3
Size check | OK
Members
Member | Name | Student ID | Role / main responsibility | % contribution | Commits (from Commit Log) | Check
Member 1 | Trần Gia Triều | 519H0245 | Documentation | 30% | 0 | No commits yet
Member 2 | Phạm Trung Nghĩa | 524H0172 | Coding and documentation | 40% | 0 | No commits yet
Member 3 | Lê Đạt | 524H0044 | Documentation | 30% | 0 | No commits yet
Member 4
Member 5
|  |  | Total contribution | 100%
|  |  | Check | OK
Contribution is the share of the whole project each member built, in agreement with the group. The lecturer may adjust it using the Git history, the pull requests and individual questions.

## Clarification Q&A
Clarification Q&A (Task 1, 5 marks)
Identify the ambiguities in the problem statement, ask the stakeholders, and give logical assumed answers to base your design on.
Q ID | Area | Ambiguity found in the problem statement | Clarifying question to the stakeholder | Stakeholder asked | Assumed answer (logical) | Rationale and impact on the design | Requirement ID | Status | Lecturer comment
Q01 | Users and accessibility | Which passenger types, routes, and fares are sold? | Who are your target clients | Transport authority | Adult single journey; operator-maintained route and fare catalogue. | Destination and fare snapshot in each ticket transaction. | FR-01, DR-02 | Final
Q02 | Ticket and fares | Are card and wallet integrations live? | how do you want the payment to be processed | Bank / payment gateway | Production uses certified providers; current demo is simulation only. | Adapter boundaries; no real charge or credentials in demo. | FR-02, NFR-06 | Final
Q03 | Failure handling | How are declined, timed-out, and duplicate payments handled? |  | Operator | Decline permits retry; timeout remains unknown until reconciliation; callbacks are idempotent. | No ticket until confirmed; unique idempotency reference. | FR-03, DR-03, DR-05 | Final
Q04 | Performance and reliability | When is a ticket valid and how is it checked? |  | Bank / payment gateway | Single journey valid for the service day; barcode holds an opaque unique ticket ID. | Unique ticket identity; no personal data in barcode. | FR-04, DR-04 | Final
Q05 | Payment | Are refund and cancellation supported? | would you want to support refund | Passenger | Cancel before payment; after capture use operator-audited reversal/refund. | Transaction state and compensation record. | FR-07, DR-07 | Final
Q06 | Users and accessibility | Which accessibility and language requirements apply? | do you want multi language support | Passenger | Vietnamese/English, high contrast, large touch targets, accessible timeout. | Bilingual UI and accessibility acceptance criteria. | NFR-07 | Final
Q07 | Security | What payment data is retained? | how much data are to be retained | Passenger | Never retain PAN, CVV, wallet credentials, or raw QR; retain masked provider reference. | Data minimization and secure audit log. | NFR-06 | Final
Q08 | Performance and reliability | What availability and response time are required? |  | Operator | 99.5% monthly kiosk availability; UI p95 <=1s; routes <=2s; payment timeout 15s. | Measurable NFRs; monitor availability and latency. | NFR-01..05 | Final
Q09 | Payment | Is cash payment required? | does the service take cash | Passenger | Out of scope; brief specifies card, QR, and wallet. | No cash hardware or cash reconciliation. | FR-02 | Final
Q10 | Failure handling | What if network or printer fails? |  | Passenger | Fail safely; no ticket before confirmed payment; reconcile, reprint, or compensate. | Fault state and recovery workflow. | FR-07, FR-08 | Final
Q11 | Integration | Which external systems are integrated? | what system do you wish to intergrate | Bank / payment gateway | Route/fare API, card acquirer, Momo/VNPay/ZaloPay, validator, monitoring. | Deployment and activity diagram actors. | FR-02, FR-03 | Final
Q12 | Other | How long are records retained? | how will the passengers record be retained? | Passenger | Non-sensitive transaction events retained 12 months, subject to operator policy. | Retention configurable; audit policy requires approval. | FR-06, NFR-06 | Final
Q13
Q14
Q15
Q16
Q17
Q18
Q19
Q20
Q21
Q22
Q23
Q24
Q25
|  | Questions written | 8
|  | Questions linked to a requirement | 12
|  | Areas covered | 8
Strong Q&A uncovers hidden complexity (timeouts, declined payments, refunds, printer or paper out, offline mode, fares). Aim for several different areas, not many questions on one topic.

## Requirements
Requirements Specification (Task 2, 15 marks)
Functional, Non-Functional and Domain requirements. Every NFR needs a measurable metric. Focus: reliability and response time.
ID | Requirement | Type | Category (NFR) | Measurable metric / fit criterion (NFR) | Measurement method | Priority | Use case | Source (Q ID) | Lecturer comment
FR-01 | Start a purchase and show active destinations and fares. | FR |  |  |  | High | Must / Q1/Q8 → UC-01/06 | FR-01
FR-02 | Select destination and card, bank QR or wallet QR payment. | FR |  |  |  | High | Must / Q2/Q9 → UC-02/03/07 | FR-02
FR-03 | Authorize using an idempotency key and handle all outcomes. | FR |  |  |  | High | Must / Q3/Q7 → UC-02/03/05 | FR-03
FR-04 | Print a barcode ticket only after confirmed payment. | FR |  |  |  | High | Must / Q4/Q10 → UC-08 | FR-04
FR-05 | Display route, fare, time, and masked reference on receipt. | FR |  |  |  | High | Must / Q4/Q7 → UC-09 | FR-05
FR-06 | Audit payment, transaction, print, and status events. | FR |  |  |  | High | Must / Q7/Q12 → UC-04/05 | FR-06
FR-07 | Recover and reconcile after interruption. | FR |  |  |  | High | Must / Q3/Q5/Q10 → UC-05 | FR-07
FR-08 | Expose operator diagnostics and kiosk out-of-service status. | FR |  |  |  | High | Must / Q10/Q11 → UC-04 | FR-08
NFR-01 | Monthly service availability excluding planned maintenance. | NFR | Reliability | >=99.5%; available scheduled minutes / total scheduled minutes. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | Medium |  | NFR-01 / Reliability
NFR-02 | Local input and screen transition. | NFR | Response time | p95 <=1 second; p99 <=2 seconds. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | High |  | NFR-02 / Performance
NFR-03 | Route/fare catalogue load. | NFR | Response time | p95 <=2 seconds; cached data timestamped, max age 24 hours. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | Medium |  | NFR-03 / Performance
NFR-04 | Payment completion or safe timeout. | NFR | Response time | 95% <=8 seconds; timeout at 15 seconds; reconcile unknown result. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | High |  | NFR-04 / Performance
NFR-05 | Print after confirmed authorization. | NFR | Reliability | Print starts <=2 seconds; failure initiates alert and compensation. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | High |  | NFR-05 / Reliability
NFR-06 | Protect payment and service data. | NFR | Security | TLS 1.2+, encrypted secrets, least privilege, no PAN/CVV, signed callbacks. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | Medium |  | NFR-06 / Security
NFR-07 | Support public touchscreen use. | NFR | Availability | Large targets >=44 px, readable contrast, bilingual UI, timeout extension. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | Medium |  | NFR-07 / Accessibility
NFR-08 | Isolate routes, gateways, persistence, and printer. | NFR | Maintainability | Ports/adapters, structured logs, documented config, automated tests. | Timed trials/logs for latency; scheduled-minute observation for availability; accessibility and security review for relevant controls | Low |  | NFR-08 / Maintainability
DR-01 | At most one ticket per confirmed payment. | DR | [5 empty] | DR-01
DR-02 | The active route fare is captured once. | DR | [5 empty] | DR-02
DR-03 | Payment references and barcodes are unique. | DR | [5 empty] | DR-03
DR-04 | Ticket QR uses an opaque ID and service-day validity. | DR | [5 empty] | DR-04
DR-05 | Unknown payments reconcile before a new attempt. | DR | [5 empty] | DR-05
DR-06 | Payment QR binds transaction, amount and method and expires. | DR | [5 empty] | DR-06
DR-07 | Printer failure requires compensation. | DR | [5 empty] | DR-07
| Functional requirements | 8
| Non-functional requirements | 8
| Domain requirements | 7
| NFRs without a measurable metric | 0
| Reliability NFRs (need at least 1) | 2
| Response-time NFRs (need at least 1) | 3
| Critical focus check | OK

## Use Cases
Use Case Register (Task 3)
One row per use case. Each needs a full description and appears in the use case diagram.
ID | Use case | Primary actor | Short description | Requirement IDs | Description written? | In activity / sequence diagram? | Owner (ID) | Lecturer comment
UC01 | UC-01 Buy ticket | Passenger | user chooses buy ticket |  | Yes | Yes
UC02 | UC-02 Pay by card | Passenger | payment method by card is chosen |  | Yes | Yes
UC03 | UC-03 Pay by bank / wallet QR | Passenger | payment method by bamk or digital wallet is chosen |  | Yes | Yes
UC04 | UC-04 Diagnose kiosk | Operator | A fault or unknown transaction needs resolution Authenticated operator and service mode. |  | Yes | Yes
UC05 | UC-05 Reconcile transaction | Operator | Query gateway; compare capture; retry print or refund. |  | Yes | Yes
UC06 | UC-06 Select destination | Passenger | passenger chooses where to go |  | Yes | Yes
UC07 | UC-07 Choose payment | Passenger | passenger chooses and confirm payment method |  | Yes | Yes
UC08 | UC-08 Print ticket | Passenger | Confirmed payment and working printer.Generate unique opaque barcode; print route, fare, validity, and barcode. |  | Yes | Yes
UC09 | UC-09 View receipt | Passenger | Show route, fare, time, reference, and support guidance. |  | Yes | Yes
UC10
UC11
UC12

## Artifact Tracker
Artifact Tracker
Track every deliverable. Percent complete is calculated from the status.
Task | Artifact | Marks | Tool | Owner (ID) | File / link | Status | % complete | Lecturer comment
1 | Clarification Q&A (Excel) | 5 | Excel |  |  | Done | 100%
2 | Requirements Specification | 15 | Excel |  |  | Done | 100%
3 | Use case diagram | 5 | DOT + PNG |  |  | Done | 100%
3 | Use case descriptions | 5 | DOT + PNG |  |  | Done | 100%
4 | Activity diagram: buy a ticket | 5 | DOT + PNG |  |  | Done | 100%
4 | Activity diagram: payment gateways | 5 | DOT + PNG |  |  | Done | 100%
5 | Sequence diagram | 5 | DOT / Python |  |  | Done | 100%
5 | State chart diagram | 5 | DOT / Python |  |  | Done | 100%
5 | Class diagram | 5 | DOT / Python |  |  | Done | 100%
6 | UI/UX wireframes or mockups | 5 | WinForms |  |  | Done | 100%
7 | Architecture diagram | 5 | WinForms |  |  | Done | 100%
7 | Deployment diagram | 5 | WinForms |  |  | Done | 100%
8 | VS forward engineering (model to code) | 4 | JSON / C# / DGML |  |  | Done | 100%
8 | VS backward engineering (code to model) | 3 | JSON / C# / DGML |  |  | Done | 100%
8 | VS Code Map | 3 | JSON / C# / DGML |  |  | Done | 100%
9 | GitHub repository with collaboration history | 5 | GitHub |  |  | Done | 100%
9 | Copilot prompt documentation | 5 |  |  |  | Done | 100%
10 | Demo: C# and MSSQL input form | 4 | C# / SQL / MSTest |  |  | Done | 100%
10 | Demo: output report or success screen | 3 | C# / SQL / MSTest |  |  | Done | 100%
10 | Demo: database script and run instructions | 3 | C# / SQL / MSTest |  |  | Done | 100%
– | Report .docx | 0 | Word |  |  | Done | 100%
– | readme.txt | 0 | GitHub |  |  | Done | 100%
– | % contribution of each member | 0 | Excel |  |  | Done | 100%
| Overall progress | 100%
| Artifacts done | 23 of 23
Marks column shows the weight of each task of the assignment (split across its artifacts for tracking only).

## Consistency Check
Model Consistency Check
Diagrams must be syntactically correct, logically sound and aligned with each other.
# | Check | Diagrams involved | Student | Lecturer | Notes
1 | Every use case in the diagram has a description, and every description is in the diagram | Use case diagram / descriptions | Yes
2 | Every step of the main flow appears in the activity diagram | Descriptions / activity | Yes
3 | Objects and messages in the sequence diagram exist as classes and methods in the class diagram | Sequence / class | Yes
4 | State names and transitions match the events in the sequence diagram | State chart / sequence | Yes
5 | Payment gateway steps match between both activity diagrams and the sequence diagram | Activity / sequence | Yes
6 | Requirement IDs are cited in the use cases | Requirements / use cases | Yes
7 | The class diagram matches the C# code from forward and backward engineering | Class / code | Yes
8 | The UI screens match the steps of the main flow | Wireframes / descriptions | Yes
9 | The architecture and deployment diagrams show the same components | Architecture / deployment | Yes
10 | UML notation is correct (arrows, multiplicities, guards, swim lanes) | All diagrams | Yes

## AI Prompt Log
AI Prompt Log (Task 9)
Document each prompt to GitHub Copilot (or a similar tool), how it helped, and how you validated the generated code.
No. | Date | Student ID | Tool | Task / artifact | Prompt used | How the AI helped (boilerplate / logic / explanation) | Output used? | How we validated it (tests, code review, run) | Lecturer comment
1 | 23 October 2026 | 524H0172 | Codex | Domain, tests, workbooks and reports | Complete PDFs and rubric | Build / MSTest / SQL demo | Kept | implementing into draft
2 | 23 October 2026 | 524H0172 | Codex | Kiosk states, original design and 30-second media | Upgrade UI/UX and functional demos | Native screenshots / browser | Kept | implementing into draft
3 | 23 October 2026 | 524H0172 | image_gen | Original artwork; timed motion graphics | Joyful MetroGo 3D transit scene | Image inspection / metadata | Rejected | implementing into draft
4 | 23 October 2026 | 524H0172 | Codex | TF-IDF guidance; read-only recommendations; three themes | Add local AI and flexible palettes | 21 A1 / 26 A2 unit tests; browser AI demo | Changed | implementing into draft
5 | 24 October 2026 | 524H0172 | Codex | Idempotent ticket SQL harness and clean fixture | Verify transactions and printable evidence | 21 unit + 5 SQL checks | Kept | implementing into draft
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
|  |  |  | Kept | 3
|  |  |  | Changed | 1
|  |  |  | Rejected | 1
|  |  |  | Used without validation | 0
Every AI output you keep or change must have a validation. The red counter shows prompts with a decision but no validation.

## Commit Log
Commit and Pull Request Log
Record the evidence of collaboration each week. Use the Student ID exactly as in the Team sheet.
Week | Date | Student ID | Branch | Commits | Pull requests | What was done / link | Lecturer comment

## Progress Log
Weekly Progress Log
Fill in at the end of each lab week. Adjust the planned work to your own schedule.
Checkpoint | Planned for this week | What we actually did | Evidence (commit / PR / screenshot link) | Blockers and help needed | Status (team) | Lecturer feedback | Checkpoint
Week 1 | Read the assignment, form the team, set up GitHub, start Clarification Q&A
Week 2 | Requirements specification (FR, NFR with metrics, domain)
Week 3 | Use case model and activity diagrams
Week 4 | Sequence, state chart, class diagram; wireframes; architecture
Week 5 | Forward and backward engineering, Code Map; demo application
Week 6 | Finish demo, report, readme.txt, self-marking
Checkpoints met | 0 of 6
Update this sheet at the end of every lab week. A short, honest record earns the process mark; a blank log does not.

## Marking
Marking: Self and Lecturer
Enter marks out of each task's Max. Yellow = student self-mark, green = lecturer mark.
No. | Task | Max (marks) | What to check for full marks | Student self-mark | Lecturer mark | Difference (self − lecturer) | Student justification / evidence | Lecturer comments
1 | Clarification Q&A (Excel) | 5 | Thorough questions uncovering hidden complexity, each with a logical assumed answer and a requirement link.
2 | Requirements Specification | 15 | Functional, non-functional and domain requirements with IDs. Strict, measurable reliability and response-time limits.
3 | Use Case Modeling | 10 | Correct use case diagram and a detailed description for every use case.
4 | Activity Diagrams | 10 | Buy-a-ticket flow with failures, and a separate payment gateway integration diagram.
5 | Detailed System Modeling: Buy a Ticket | 15 | Sequence, state chart and class diagram: correct, logical and aligned with each other.
6 | UI/UX Design | 5 | Modern, intuitive wireframes or mockups for the TVM screens.
7 | Architectural Design | 10 | Logical, modular architecture (MVC or system-in-a-box) suited to the hardware; deployment diagram with API context.
8 | Visual Studio Engineering | 10 | Forward engineering, backward engineering and a Code Map, all shown and explained.
9 | GitHub & AI Tooling (Copilot) | 10 | Rich commit history from all members; Copilot prompts documented with validation of the output.
10 | Demo Application (C# and MSSQL) | 10 | Runs smoothly: input form and output report or success screen for the ticket buying flow.
| Total (/100) | 100 |  | 0 | 0 | 0
A red difference means self-mark and lecturer mark differ by more than 20% of the task's Max: discuss it in the feedback session.

## Summary
Group Summary and Results
Results are calculated from the Marking sheet.
Group name
Weight of this assignment in QT2 | 20%
Marked by / date
Group results
Measure | Student self-marking | Lecturer | Difference
Total (/100) | 0 | 0 | 0
Contribution to QT2 (points) | 0 | 0 | 0
Bonus point toward the Final Project (lecturer, 0 or 1)
Individual marks
Member | Student ID | % contribution | Lecturer adjustment factor (0.70-1.00, blank = 1) | Individual mark (/100) | Individual QT2 points
Trần Gia Triều | 519H0245 | 30% |  | 0 | 0
Phạm Trung Nghĩa | 524H0172 | 40% |  | 0 | 0
Lê Đạt | 524H0044 | 30% |  | 0 | 0
The factor is reduced below 1.00 only when the evidence (Git history, pull requests, progress log, individual questions) shows a clearly smaller contribution.
Comments
Student reflection (optional)
Lecturer feedback